## Title page
Assignment: SDLC for human activity recognition project

## Product backlog
Product backlog
ID | Feature | User | Reason | Priority | Status
1 | Load dataset | Model | Allow the model to read test data | 1 | Complete
2 | Visualize data | User | To interperet the data | 2 | Complete
3 | Remove signal noise | User | Display vizually concise and assist with interpreting the data | 3 | Incomplete
4 | Extract features | Model | Separate the data and categorise them for the model | 4 | Incomplete
5 | Prepare training set | Model | Provide input for processing | 5 | Incomplete
6 | Train models | Model | Feed input for machine learning | 6 | Incomplete
7 | Test models | Model | Observe and fix boundary cases that may cause unintended faults, failures and errors | 7 | Incomplete
8 | Print evaluation result | User | To observe the results when the model is given input | 8 | Incomplete

## Sprint backlog
Sprint Backlog
ID | Priority | Feature | Assigned Sprint | Estimated time (hrs.) | Sprint 1 (Sep 10-11th) | Sprint 2 (Sep 11-12th) | Sprint 3 (Sep 12-13th) | Sprint 4 (Sep 13-14th) | Sprint 5 (Sep 14-15th)
1 | 1 | Load dataset | 1 | 8 | 3
2 | 2 | Vizualize data | 1 | 4 | 3
3 | 3 | Remove signal noise | 2 | 4
4 | 4 | Extract features | 2 | 8
5 | 5 | Prepare training set | 3 | 2
6 | 6 | Train models | 3 | 8
7 | 7 | Test models | 4 | 8
8 | 8 | Print evaluation result | 4 | 4

## Sprint 1
Sprint 1
ID | Priority | Feature | User | Reason | Time hrs (Sep 10th-11th) | Estimated time remaining (hrs) | Actual time remaining (hrs)
1 | 1 | Load dataset | Model | Allow the model to read test data | 0:00 | 12 | 12
2 | 2 | Visualize data | User | To interperet the data | 1:00 | 12 | 12
[5 empty] | 2:00 | 12 | 12
[5 empty] | 3:00 | 12 | 12
[5 empty] | 4:00 | 12 | 12
[5 empty] | 5:00 | 12 | 12
[5 empty] | 6:00 | 12 | 12
[5 empty] | 7:00 | 12 | 12
[5 empty] | 8:00 | 11 | 12
[5 empty] | 9:00 | 10 | 12
[5 empty] | 10:00 | 9 | 12
[5 empty] | 11:00 | 9 | 12
[5 empty] | 12:00 | 9 | 12
[5 empty] | 13:00 | 9 | 12
[5 empty] | 14:00 | 9 | 12
[5 empty] | 15:00 | 9 | 12
[5 empty] | 16:00 | 8 | 12
[5 empty] | 17:00 | 7 | 12
[5 empty] | 18:00 | 6 | 12
[5 empty] | 19:00 | 5 | 12
[5 empty] | 20:00 | 4 | 12
[5 empty] | 21:00 | 3 | 12
[5 empty] | 22:00 | 2 | 11
[5 empty] | 23:00 | 1 | 9
[5 empty] | 24:00 | 0 | 6
5
3
0

## Sprint 2
Sprint 1
ID | Priority | Feature | User | Reason | Time hrs (Sep 10th-11th) | Estimated time remaining (hrs) | Actual time remaining (hrs)
1 | 1 | Load dataset | Model | Allow the model to read test data | 0:00 | 12 | 12
2 | 2 | Visualize data | User | To interperet the data | 1:00 | 12 | 12
[5 empty] | 2:00 | 12 | 12
[5 empty] | 3:00 | 12 | 12
[5 empty] | 4:00 | 12 | 12
[5 empty] | 5:00 | 12 | 12
[5 empty] | 6:00 | 12 | 12
[5 empty] | 7:00 | 12 | 12
[5 empty] | 8:00 | 12 | 12
[5 empty] | 9:00 | 12 | 12
[5 empty] | 10:00 | 12 | 12
[5 empty] | 11:00 | 12 | 12
[5 empty] | 12:00 | 12
[5 empty] | 13:00 | 11
[5 empty] | 14:00 | 10
[5 empty] | 15:00 | 9
[5 empty] | 16:00 | 8
[5 empty] | 17:00 | 7
[5 empty] | 18:00 | 6
[5 empty] | 19:00 | 5
[5 empty] | 20:00 | 4
[5 empty] | 21:00 | 3
[5 empty] | 22:00 | 2
[5 empty] | 23:00 | 1
[5 empty] | 24:00 | 0