## Title page
Assignment: SDLC for human activity recognition project

## Product backlog
Product backlog
ID | Feature | User | Reason | Priority | Status
1 | Load dataset | Model | Allow the model to read test data | 1 | Incomplete
2 | Vizualize data | User | To interperet the data | 2 | Incomplete
3 | Remove signal noise | User | Display vizually concise and assist with interpreting the data | 3 | Incomplete
4 | Extract features | Model | Separate the data and categorise them for the model | 4 | Incomplete
5 | Prepare training set | Model | Provide input for processing | 5 | Incomplete
6 | Train models | Model | Feed input for machine learning | 6 | Incomplete
7 | Test models | Model | Observe and fix boundary cases that may cause unintended faults, failures and errors | 7 | Incomplete
8 | Print evaluation result | User | To observe the results when the model is given input | 8 | Incomplete

## Sprint backlog
Sprint Backlog
ID | Priority | User Stories | Assigned Sprint | Estimated time (hrs.) | Sprint 1 (Sep 10-11th) | Sprint 2 (Sep 11-12th) | Sprint 3 (Sep 12-13th) | Sprint 4 (Sep 13-14th) | Sprint 5 (Sep 14-15th)
1 | 1 | Load dataset | 1 | 8
2 | 2 | Vizualize data | 1 | 4
3 | 3 | Remove signal noise | 2 | 4
4 | 4 | Extract features | 2 | 8
5 | 5 | Prepare training set | 3 | 2
6 | 6 | Train models | 3 | 8
7 | 7 | Test models | 4 | 8
8 | 8 | Print evaluation result | 4 | 4